## Hárok1
IT Project Risk Database (based on ISO/IEC/IEEE 16085:2020)
Version: 18.10.2020
[5 empty] | Risk Analysis / Measure | [7 empty] | Residual Risk Analysis (after Action adopted)
Process Group |  | Process |  | Typical Risk | Probabaility | Impact | Risk Exposure | Response | Action | Responsible | Deadline | Status / Result | Probabaility | Impact | Risk Exposure | Status / Result
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Lack of clarity of agreements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Lack of feasibility in the parameters of agreement (e.g., infeasible cost, schedule, or outcomes) | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Poor acquisition strategy | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Poor understanding of acceptance processes between the parties | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Acquirers that do not actively participate their projects | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Acquirers not taking responsibilities for the definition of system requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Acquirers not taking responsibilities for the definition of software requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Acquirers that make no effort to take accountability for requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Features or functions are requested that are not in the established agreement | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Proceeding without stakeholder agreement on defined requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Misunderstood requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.01 | Agreement Processes | 7.2.2 | Acquisition Process | Failure to review and negotiate agreement details | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.02 | Agreement Processes | 7.2.3 | Supply Process | The response to the acquirer’s request is infeasible | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.02 | Agreement Processes | 7.2.3 | Supply Process | Mismatch between acquirer’s knowledge of needs versus supplier’s knowledge of feasibility andcost drivers for solution | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.02 | Agreement Processes | 7.2.3 | Supply Process | Proceeding to the next step without agreement among stakeholders | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.02 | Agreement Processes | 7.2.3 | Supply Process | Agreements do not allow for change | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.02 | Agreement Processes | 7.2.3 | Supply Process | Incomplete requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.02 | Agreement Processes | 7.2.3 | Supply Process | Not fully understanding the requirement as written | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.02 | Agreement Processes | 7.2.3 | Supply Process | Interpretation of terminology is different | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
AGR.02 | Agreement Processes | 7.2.3 | Supply Process | Supplier assumptions do not match acquirers | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.01 | Organizational project-enabling processes | 7.3.2 | Life cycle model management process | The organization's life cycle processes, good by themselves, do not work together well enough, putting the value of the organization's systems and software engineering project results at risk | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.01 | Organizational project-enabling processes | 7.3.2 | Life cycle model management process | Building silos, overlaps, and sub-optimization | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.01 | Organizational project-enabling processes | 7.3.2 | Life cycle model management process | Processes are intertwined to a degree that observers and practitioners find the processes hard to unwind. Risk management therefore also addresses an organization's life cycle processes as a whole | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.01 | Organizational project-enabling processes | 7.3.2 | Life cycle model management process | Mismatch of lifecycle model to problem space | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.02 | Organizational project-enabling processes | 7.3.3 | Infrastructure management process | The infrastructure will not meet project needs, since the project either ignored the infrastructure or poorly specified the infrastructure requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.02 | Organizational project-enabling processes | 7.3.3 | Infrastructure management process | Timing of infrastructure availability is inappropriate | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.03 | Organizational project-enabling processes | 7.3.4 | Portfolio management process | Projects are mismatched, misaligned in time, or overlap in scope | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.03 | Organizational project-enabling processes | 7.3.4 | Portfolio management process | Realizing that a project may not be viable | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.04 | Organizational project-enabling processes | 7.3.5 | Human resource management process | Inadequate skills | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.04 | Organizational project-enabling processes | 7.3.5 | Human resource management process | Insufficient resources | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.04 | Organizational project-enabling processes | 7.3.5 | Human resource management process | Inadequate training | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.04 | Organizational project-enabling processes | 7.3.5 | Human resource management process | Insufficient or outdated knowledge and skills inventory | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.05 | Organizational project-enabling processes | 7.3.6 | Quality management process | The "Evaluate quality management" activity is often not done well. Specifically, often there is little or no history of quality assurance evaluation results | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.05 | Organizational project-enabling processes | 7.3.6 | Quality management process | Establishing quality management procedures that are too burdensome for the project so that extra resources are required to staff the quality assurance activities | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.05 | Organizational project-enabling processes | 7.3.6 | Quality management process | Not listening to the management of the project teams or not implementing their suggestions | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.05 | Organizational project-enabling processes | 7.3.6 | Quality management process | Overly complex assurance processes may defeat their intent | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.05 | Organizational project-enabling processes | 7.3.6 | Quality management process | Helping assure the quality process and procedures are sufficient for the project | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.05 | Organizational project-enabling processes | 7.3.6 | Quality management process | The existing quality management process has not changed based on lessons identified on other projects | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.05 | Organizational project-enabling processes | 7.3.6 | Quality management process | Lack of independence for quality management personnel | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.06 | Organizational project-enabling processes | 7.3.7 | Knowledge management process | Incomplete or inaccurate inventory of organizational knowledge and skills | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.06 | Organizational project-enabling processes | 7.3.7 | Knowledge management process | Lack of knowledge needs for the present and future | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
ORG.06 | Organizational project-enabling processes | 7.3.7 | Knowledge management process | Understanding how to capture tacit knowledge such as intuitive skills | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Insufficient or incorrect identification of project scope, objectives, and constraints | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Inconsistent or changing scope of the project | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Inadequate definition and maintenance of project structure including life cycle models, work breakdown structure, and processes | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Insufficient subject matter experts in the requirements, design, development, verification, or validation activities | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Insufficient or incorrect development method, environment and tools | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Unintended consequences and additional uncertainties related to repeated changes in scope, objectives and constraints, and excessive unanticipated re-planning and rework | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Using a rough estimate written in the early phase through the whole lifecycle without reviews | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Inappropriate level of detail | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Invalid assumptions | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Estimations that lack rationale | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Estimations that lack proper scope | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Insufficient focus on the development of the operational system | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.01 | Technical management processes | 7.4.2 | Project planning process | Lack of consideration of sustainment of system | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.02 | Technical management processes | 7.4.3 | Project assessment and control process | Incomplete or inaccurate business needs and requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.02 | Technical management processes | 7.4.3 | Project assessment and control process | Incomplete or inaccurate assessment results | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.02 | Technical management processes | 7.4.3 | Project assessment and control process | Vague plans | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.02 | Technical management processes | 7.4.3 | Project assessment and control process | Inappropriate reviews | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.02 | Technical management processes | 7.4.3 | Project assessment and control process | Unclear review goals | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.02 | Technical management processes | 7.4.3 | Project assessment and control process | periodic reviews not held or period between reviews is insufficient to control processes (for example, one per year is probably not enough for most programs) | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.02 | Technical management processes | 7.4.3 | Project assessment and control process | significant deviations and variations are not detected | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.02 | Technical management processes | 7.4.3 | Project assessment and control process | projects that consume excessive resources and are over budget, late, or lacking acceptable quality deliverables | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.03 | Technical management processes | 7.4.4 | Decision management process | Decision making approach has not been agreed upon and approved by all stakeholders | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.03 | Technical management processes | 7.4.4 | Decision management process | Timely decisions are not made | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.03 | Technical management processes | 7.4.4 | Decision management process | Decisions are not based on accurate information | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.03 | Technical management processes | 7.4.4 | Decision management process | All relevant stakeholders are not included in the decision making | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.04 | Technical management processes | 7.4.5 | Risk management process | Inappropriate or insufficient risk categories | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.04 | Technical management processes | 7.4.5 | Risk management process | Inappropriate or insufficient risk thresholds | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.04 | Technical management processes | 7.4.5 | Risk management process | Focus is only on projects and not the organization, products, and services | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.04 | Technical management processes | 7.4.5 | Risk management process | All critical risks are not identified | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.04 | Technical management processes | 7.4.5 | Risk management process | Risk likelihood of occurrence or consequence are estimated incorrectly | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Planned baselines are not clearly defined when the project starts | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Baselines are not established or maintained | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Controlled items are not identified | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Current status of development or individual product instances is unknown | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Baselines are not reviewed for integrity | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Teams work to different baselines without clear management direction to do so | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Baselines are unclear | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Variation and change are not explicitly managed | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | All required items are not included in the CM process | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Complete inventory of system and software components is not available when needed | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Users circumvent the process and fail to update items when changed | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Suppliers are not made aware of changes | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | CM controls do not protect the integrity of items maintained in the CM libraries | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Changes to baselines are made without understanding the impact of the change on other aspects of the program (e.g. cost, schedule, affected products, interfaces) | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.05 | Technical management processes | 7.4.6 | Configuration management process | Consistency issues when using multiple CM systems | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.06 | Technical management processes | 7.4.7 | Information management process | Not appropriately communicating and disseminating the purpose of the project and project documents to all relevant stakeholders | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.06 | Technical management processes | 7.4.7 | Information management process | Information is inconsistent, incorrect, or misleading | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.06 | Technical management processes | 7.4.7 | Information management process | The form of the information is inappropriate | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.07 | Technical management processes | 7.4.8 | Measurement process | Measuring everything | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.07 | Technical management processes | 7.4.8 | Measurement process | Not making key measurements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.07 | Technical management processes | 7.4.8 | Measurement process | Lack of what was measured | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.07 | Technical management processes | 7.4.8 | Measurement process | Inconsistent measurement within and between projects | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.07 | Technical management processes | 7.4.8 | Measurement process | Measurement are used inappropriately (for example. used to measure personnel’s performance) | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.08 | Technical management processes | 7.4.9 | Quality assurance process | If there are multiple test teams, the risk of not checking each team's testing and reporting | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.08 | Technical management processes | 7.4.9 | Quality assurance process | Performing quality assurance on all activities in the process | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.08 | Technical management processes | 7.4.9 | Quality assurance process | Failure to identify processes and procedures that should have been applied to the project | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
MAN.08 | Technical management processes | 7.4.9 | Quality assurance process | Failure to identify project non-compliance with procedures | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.01 | Technical processes | 7.5.2 | Business or mission analysis process | Lack of organizational and project business strategy | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.01 | Technical processes | 7.5.2 | Business or mission analysis process | Unclear problem definition or boundaries | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.01 | Technical processes | 7.5.2 | Business or mission analysis process | Lack of understanding of the total cost of the system | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Insufficient or incorrect identification of stakeholders | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Stakeholder requirements that do not satisfy the business requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Established stakeholder requirements that are ignored during later lifecycle stages | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Unidentified and unresolved conflicts and inconsistencies in stakeholder needs and requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Level of abstraction/detail too high or low (i.e., mismatched to problem space and purpose of requirements in acquisition or supply process) | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Inadequate identification and definition of stakeholder needs and requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Inadequate communication and understanding of stakeholder needs and requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Unidentified and unresolved conflicts and inconsistencies in stakeholder needs and requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Suppliers and other stakeholders are not included when defining requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Lack of operational requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.02 | Technical processes | 7.5.3 | Stakeholder needs and requirements definition process | Unrealistic requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | Stakeholders needs and requirements were insufficiently or inaccurately captured | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | Postponing requirement definitions that are critical to project success | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | Requirements are too vague and can be interpreted in different ways | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | Established software/system requirements that are ignored | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | Everyone measures the non-quantified requirements differently | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | System/software requirements that do not satisfy the stakeholder requirements or business requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | Requirements that go beyond the stakeholder needs and business requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | System/software requirements containing the phrase "just the same as the present.” The term same is interpreted correctly only if it is about existing, discrete, tangible objects such as software programs | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | Sudden growth in requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | Interfaces with other systems and with humans were not understood or defined | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | Different priorities and weights of requirements were not shared with all stakeholders | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | Requirements are not able to be verified and validated | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.03 | Technical processes | 7.5.4 | System/Software requirements definition process | There is a significant amount of requirements rework as project progresses ("scope creep") | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.04 | Technical processes | 7.5.5 | Architecture definition process | Solution is incomplete and does not meet all the requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.04 | Technical processes | 7.5.5 | Architecture definition process | Incomplete properties and relationships | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.04 | Technical processes | 7.5.5 | Architecture definition process | Multiple system configurations that causes architectural complexity | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.04 | Technical processes | 7.5.5 | Architecture definition process | Architecture inadvertently constrains future direction or growth of the system | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.04 | Technical processes | 7.5.5 | Architecture definition process | Interfaces with other systems and with humans are not incorporated into architecture | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.04 | Technical processes | 7.5.5 | Architecture definition process | Interfaces are not defined correctly | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.05 | Technical processes | 7.5.6 | Design definition process | Incomplete design | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.05 | Technical processes | 7.5.6 | Design definition process | Unclear or incomplete specification of requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.05 | Technical processes | 7.5.6 | Design definition process | Rushing through the design process | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.05 | Technical processes | 7.5.6 | Design definition process | Not address non-functional requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.05 | Technical processes | 7.5.6 | Design definition process | Compromising on design to meet resource constraints | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.05 | Technical processes | 7.5.6 | Design definition process | Complex design that exceeds the needs of the requirements and architecture | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.05 | Technical processes | 7.5.6 | Design definition process | Not addressing all functional requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.05 | Technical processes | 7.5.6 | Design definition process | Lack of design documentation to support maintenance | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.05 | Technical processes | 7.5.6 | Design definition process | Design not maintained current with requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.05 | Technical processes | 7.5.6 | Design definition process | Reducing functionality to compensate for cost and schedule overruns | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.06 | Technical processes | 7.5.7 | System analysis process | Only examining a subset of systems critical to the project | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.06 | Technical processes | 7.5.7 | System analysis process | Improperly quantified assumptions based on inadequate input | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.06 | Technical processes | 7.5.7 | System analysis process | Use of biased algorithms | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.06 | Technical processes | 7.5.7 | System analysis process | Differences between simulated time scale(s) and actual real time | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.07 | Technical processes | 7.5.8 | Implementation process | Implementation begins before development, verification, and integration activities are sufficiently complete | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.08 | Technical processes | 7.5.9 | Integration process | Not finding problems earlier when they are easier to fix | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.08 | Technical processes | 7.5.9 | Integration process | Missing requirements and interfaces | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.08 | Technical processes | 7.5.9 | Integration process | Incomplete or inadequate integration activities | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.08 | Technical processes | 7.5.9 | Integration process | Lack of supporting infrastructure for integration | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.08 | Technical processes | 7.5.9 | Integration process | Lack of structured integration process | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.08 | Technical processes | 7.5.9 | Integration process | System components including software are not tested as planned before being moved to integration | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.09 | Technical processes | 7.5.10 | Verification process | Lack of updated requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.09 | Technical processes | 7.5.10 | Verification process | Verification activities are not using the current requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.09 | Technical processes | 7.5.10 | Verification process | Verification activities are not being performed with a consistent and relevant set of work products (requirements, architecture, design, prototype, and test cases) | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.09 | Technical processes | 7.5.10 | Verification process | Poor management of identified issues | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.09 | Technical processes | 7.5.10 | Verification process | Verification only occurs during testing | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.09 | Technical processes | 7.5.10 | Verification process | Reviews are not performed during early stages of the lifecycle | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.10 | Technical processes | 7.5.11 | Transition process | Complex interactions between integration, verification and validation, transition, and acceptance processes are poorly defined or planned | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.10 | Technical processes | 7.5.11 | Transition process | Transition takes too long resulting in delay of organizational operations | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.10 | Technical processes | 7.5.11 | Transition process | Loss or corruption of data during transition | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.10 | Technical processes | 7.5.11 | Transition process | Incomplete configuration is transitioned, missing some components | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.10 | Technical processes | 7.5.11 | Transition process | No possibility to roll back in the event of transition failure | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.10 | Technical processes | 7.5.11 | Transition process | Users are unable or unwilling to work with the new system | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.10 | Technical processes | 7.5.11 | Transition process | Interfaces with external systems are inactivated | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.11 | Technical processes | 7.5.12 | Validation process | Validation environment is not available | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.11 | Technical processes | 7.5.12 | Validation process | Validation is only performed in the later lifecycle stages of a project | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.11 | Technical processes | 7.5.12 | Validation process | Validation is not performed before and after transition | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.11 | Technical processes | 7.5.12 | Validation process | Sufficient time was not scheduled for validation activities prior to system installation | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.11 | Technical processes | 7.5.12 | Validation process | Factory Acceptance Test or Qualification Tests were not conducted due to schedule constraints | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.11 | Technical processes | 7.5.12 | Validation process | Accelerated aging testing time for validation is shortened from actual lifetime of the system | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.12 | Technical processes | 7.5.13 | Operation process | Poor system usability | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.12 | Technical processes | 7.5.13 | Operation process | Failure to achieve business/mission outcomes | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.12 | Technical processes | 7.5.13 | Operation process | System used outside its planned design envelope | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.12 | Technical processes | 7.5.13 | Operation process | Not simulating Operations early enough in the project | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.12 | Technical processes | 7.5.13 | Operation process | Operational service is interrupted or compromised due to disaster, loss of power, security attacks, or insufficient capacity | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.12 | Technical processes | 7.5.13 | Operation process | Time lag (also known as latency) between remote operation and actual system activation resulting from effect of various operating conditions | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.13 | Technical processes | 7.5.14 | Maintenance process | System is not designed for efficient maintenance | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.13 | Technical processes | 7.5.14 | Maintenance process | Maintenance does not maintain alignment with architectural intent | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.13 | Technical processes | 7.5.14 | Maintenance process | Maintenance needs and requirements are not considered early in the project | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.13 | Technical processes | 7.5.14 | Maintenance process | Poorly documented system impedes problem analysis | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.13 | Technical processes | 7.5.14 | Maintenance process | Extended system lifespan reduces skilled maintenance sources | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.14 | Technical processes | 7.5.15 | Disposal process | Excessive cost of disposal | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.14 | Technical processes | 7.5.15 | Disposal process | Resources needed for disposal significantly exceed estimates | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
TEC.14 | Technical processes | 7.5.15 | Disposal process | Environmental risks of improper disposal of system components including loss of intellectual property and exposure of personal data | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
n.a. | Tailoring | 7.6 | Tailoring process | Tailoring everything | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
n.a. | Tailoring | 7.6 | Tailoring process | Insufficient tailoring guidelines for what can be changed and how much | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
n.a. | Tailoring | 7.6 | Tailoring process | Standard process was insufficiently changed to meet the project requirements | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
n.a. | Tailoring | 7.6 | Tailoring process | Not tailoring based on risk | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
n.a. | Tailoring | 7.6 | Tailoring process | The process is written at a high level and tailoring is not implied; the impact to the project is that the processes may not provide enough direction and insight to manage the project | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1